## Slide 1: Software Project Management
Mesut Ensar Erenoğlu

## Slide 2: lntroduction
1 lntroduction to software project management
2 Project evaluation
3 An overview of project planning
4 Selection of an appropriate project approach
8 Software effort estimation
7 Activity planning
6 Risk management
5 Resource allocation
9 Monitoring and control
10 Managing contracts
11 Managing people in software environments
12 Working in teams
l3 Software quality

## Slide 3: Step 1 establish project scope and objectives
1.1 Identify objectives and measures of effectiveness
‘how do we know if we have succeeded?’
1.2 Establish a project authority
‘who is the boss?’
1.3 Identify all stakeholders in the project and their interests
‘who will be affected/involved in the project?’

## Slide 4: Step 1 continued
1.4 Modify objectives in the light of stakeholder analysis
‘do we need to do things to win over stakeholders?’
1.5 Establish methods of communication with all parties
‘how do we keep in contact?’

## Slide 5: Step 2 Establish project infrastructure
2.1 Establish link between project and any strategic plan
‘why did they want the project?’
2.2 Identify installation standards and procedures
‘what standards do we have to follow?’
2.3. Identify project team organization
‘where do I fit in?’

## Slide 6: Step 3 Analysis of project characteristics
3.1 Distinguish the project as either objective or product-based.
Is there more than one way of achieving success?
3.2 Analyse other project characteristics (including quality based ones)
what is different about this project?

## Slide 7: Step 3 continued
3.3 Identify high level project risks
‘what could go wrong?’
‘what can we do to stop it?’
3.4 Take into account user requirements concerning implementation
3.5 Select general life cycle approach
waterfall? Increments? Prototypes?
3.6 Review overall resource estimates
‘does all this increase the cost?’

## Slide 8: Step 4 Identify project products and activities
4.1 Identify and describe project products - ‘what do we have to produce?’
4.2 document generic product flows
4.3 Recognize product instances
4.4. Produce ideal activity network
4.5 Add check-points if needed

## Slide 9: Step 5:Estimate effort for each activity
5.1 Carry out bottom-up estimates
distinguish carefully between effort and elapsed time
5.2. Revise plan to create controllable activities
break up very long activities into a series of smaller ones
bundle up very short activities (create check lists?)

## Slide 10: Step 6: Identify activity risks
6.1.Identify and quantify risks for activities
damage if risk occurs (measure in time lost or money)
likelihood if risk occurring
6.2. Plan risk reduction and contingency measures
risk reduction: activity to stop risk occurring
contingency: action if risk does occur
6.3 Adjust overall plans and estimates to take account of risks
e.g. add new activities which reduce risks associated with other activities e.g. training, pilot trials, information gathering

## Slide 11: Step 7: Allocate resources
7.1 Identify and allocate resources to activities
7.2 Revise plans and estimates to take into account resource constraints
e.g. staff not being available until a later date
non-project activities

## Slide 12: Step 8: Review/publicise plan
8.1 Review quality aspects of project plan
8.2 Document plan and obtain agreement
Step 9 and 10: Execute plan and create lower-level plans

## Slide 13: Effort Estimation
COCOMO II The core model is: pm = A(size)(sf) ×(em1) ×(em2) ×(em3)….
where pm = person months, A is 2.94, size is number of thousands of lines of code, sf is the scale factor, and em is an effort multiplier

## Slide 14: COCOMO II
Precedents (PREC). Degree to which there are past examples that can be consulted
Development flexibility (FLEX). Degree of flexibility that exists when implementing the project
Architecture/risk resolution (RESL). Degree of uncertainty about requirements
Team cohesion (TEAM).
Process maturity (PMAT)

## Slide 15: COCOMO II Scale factor values
Driver | Very low | Low | Nom-inal | High | Very high | Extra high
PREC | 6.20 | 4.96 | 3.72 | 2.48 | 1.24 | 0.00
FLEX | 5.07 | 4.05 | 3.04 | 2.03 | 1.01 | 0.00
RESL | 7.07 | 5.65 | 4.24 | 2.83 | 1.41 | 0.00
TEAM | 5.48 | 4.38 | 3.29 | 2.19 | 1.10 | 0.00
PMAT | 7.80 | 6.24 | 4.68 | 3.12 | 1.56 | 0.00

## Slide 16: Example of scale factor
A software development team is developing an application which is very similar to previous ones it has developed.
A very precise software engineering document lays down very strict requirements. PREC is very high (score 1.24).
FLEX is very low (score 5.07).
The good news is that these tight requirements are unlikely to change (RESL is high with a score 2.83).
The team is tightly knit (TEAM has high score of 2.19), but processes are informal (so PMAT is low and scores 6.24)

## Slide 17: Scale factor calculation
The formula for sf is
sf = B + 0.01 × Σ scale factor values
i.e. sf = 0.91 + 0.01
× (1.24 + 5.07 + 2.83 + 2.19 + 6.24)
= 1.0857
If system contained 10 kloc then estimate would be 2.94 x 101.0857 = 35.8 person months

## Slide 18: Effort multipliers
As well as the scale factor effort multipliers are also assessed:
RCPX Product reliability and complexity
RUSE Reuse required
PDIF Platform difficulty
PERS Personnel capability
FCIL Facilities available
SCED Schedule pressure

## Slide 19: Effort multipliers
 | Extra low | Very low | Low | Nom-inal | High | Very high | Extra high
RCPX | 0.49 | 0.60 | 0.83 | 1.00 | 1.33 | 1.91 | 2.72
RUSE |  |  | 0.95 | 1.00 | 1.07 | 1.15 | 1.24
PDIF |  |  | 0.87 | 1.00 | 1.29 | 1.81 | 2.61
PERS | 2.12 | 1.62 | 1.26 | 1.00 | 0.83 | 0.63 | 0.50
PREX | 1.59 | 1.33 | 1.12 | 1.00 | 0.87 | 0.74 | 0.62
FCIL | 1.43 | 1.30 | 1.10 | 1.00 | 0.87 | 0.73 | 0.62
SCED |  | 1.43 | 1.14 | 1.00 | 1.00 | 1.00 | 

## Slide 20: Activity Planning
Activity ‘write report software’
Earliest start (ES)
Earliest finish (EF) = ES + duration
Latest finish (LF) = latest task can be completed without affecting project end Latest start = LF - duration
Earliest start
Latest start
Latest
finish
activity
Earliest finish

## Slide 21: Pert Chart
Activity label, activity description
Duration
Earliest
start
Earliest
finish
Latest
start
Latest
finish
Float

## Slide 22: Resources
These include
  labour
  equipment (e.g. workstations)
  materials
  space
  services
Time: elapsed time can often be reduced by adding more staff
Money: used to buy the other resources

## Slide 23: Resource allocation
Identify the resources needed for each activity and create a resource requirement list
Identify resource types - individuals are interchangeable within the group (e.g. ‘VB programmers’ as opposed to ‘software developers’)
Allocate resource types to activities and examine the resource histogram

## Slide 24: Resource histogram: systems analysts
WEEK
1
2
3
4
5
6
7
1
2
3
4
5
STAFF REQD.

## Slide 25: Resource smoothing
It is usually difficult to get specialist staff who will work odd days to fill in gaps – need for staff to learn about application etc
Staff often have to be employed for a continuous block of time
Therefore desirable to employ a constant number of staff on a project – who as far as possible are fully employed
Hence need for resource smoothing

## Slide 26: Resource smoothing
WEEK
1
2
3
4
5
6
7
1
2
3
4
5
STAFF REQD.
8

## Slide 27: Becoming a team
Five basic stages of development:
Forming
Storming
Norming
Peforming
Adjourning
Classification associated with Tuckman and Jensen

## Slide 28: Balanced teams
Meredith Belbin studied the performance of top executives carrying out group work at the Hendon Management Centre
Tried putting the ‘best’ people together in ‘Apollo’ teams – almost invariably did badly
Identified the need for a balance of skills and management roles in a successful team

## Slide 29: Managing People in software environments
The co-ordinator – good at chairing meetings
The ‘plant’ – an idea generator
The monitor-evaluator – good at evaluating ideas
The shaper – helps direct team’s efforts
The team worker – skilled at creating a good working environment

## Slide 30: Belbin management roles - continued
The resource investigator – adept at finding resources, including information
The completer-finisher – concerned with getting tasks completed
The implementer – a good team player who is willing to undertake less attractive tasks if they are needed for team success
The specialist – the ‘techie’ who likes to acquire knowledge for its own sake

## Slide 31: Scrum
Named as an analogy to a rugby scrum – all pushing together
Originally designed for new product development where ‘time-to-market’ is important
‘Sprints’ increments of typically one to four weeks
Daily ‘scrums’ – daily stand-up meetings of about 15 minutes

## Slide 32: ISO 9126 software qualities

## Slide 33: Risk identification
Approaches to identifying risks include:
Use of checklists – usually based on the experience of past projects
Brainstorming – getting knowledgeable stakeholders together to pool concerns
Causal mapping – identifying possible chains of cause and effect

## Slide 34: Boehm’s top 10 development risks
Risk | Risk reduction techniques
Personnel shortfalls | Staffing with top talent; job matching; teambuilding; training and career development; early scheduling of key personnel
Unrealistic time and cost estimates | Multiple estimation techniques; design to cost; incremental development; recording and analysis of past projects; standardization of methods
Developing the wrong software functions | Improved software evaluation; formal specification methods; user surveys; prototyping; early user manuals
Developing the wrong user interface | Prototyping; task analysis; user involvement

## Slide 35: Boehm’s top ten risk - continued
Gold plating | Requirements scrubbing, prototyping, design to cost
Late changes to requirements | Change control, incremental development
Shortfalls in externally supplied components | Benchmarking, inspections, formal specifications, contractual agreements, quality controls
Shortfalls in externally performed tasks | Quality assurance procedures, competitive design etc
Real time performance problems | Simulation, prototyping, tuning
Development technically too difficult | Technical analysis, cost-benefit analysis, prototyping , training

## Slide 36: Risk planning
Risks can be dealt with by:
Risk acceptance
Risk avoidance
Risk reduction
Risk transfer
Risk mitigation/contingency measures

## Slide 37: Risk prioritization
Risk exposure (RE)
= (potential damage) x (probability of occurrence)
Ideally
Potential damage: a money value e.g. a flood would cause £0.5 millions of damage
Probability 0.00 (absolutely no chance) to 1.00 (absolutely certain) e.g. 0.01 (one in hundred chance)
RE = £0.5m x 0.01 = £5,000
Crudely analogous to the amount needed for an insurance premium

## Slide 38: Risk probability: qualitative descriptors
Probability level | Range
High | Greater than 50% chance of happening
Significant | 30-50% chance of happening
Moderate | 10-29% chance of happening
Low | Less than 10% chance of happening

## Slide 39: Qualitative descriptors of impact on cost and associated range values
Impact level | Range
High | Greater than 30% above budgeted expenditure
Significant | 20 to 29% above budgeted expenditure
Moderate | 10 to 19% above budgeted expenditure
Low | Within 10% of budgeted expenditure.

## Slide 40: Risk reduction leverage
Risk reduction leverage =
(REbefore- REafter)/ (cost of risk reduction)
REbeforeis risk exposure before risk reduction e.g. 1% chance of a fire causing £200k damage
REafter is risk exposure after risk reduction e.g. fire alarm costing £500 reduces probability of fire damage to 0.5%
RRL = (1% of £200k)-(0.5% of £200k)/£500 = 2
RRL > 1.00 therefore worth doing

## Slide 41: Reference
Software Project Management (Fifth Edition)
Bob Hughes and Mike Cotterell

## Slide 42: Thank You